## Gantt Chart
Task ID | Task Name | Owner | ILO | Days | Start | End | W1 02/02 | W2 02/09 | Break 02/14 | W3 02/23 | W4 03/02 | W5 03/09 | W6 03/16 | W7 03/23 | W8 03/30
SPRINT 1: Planning & Baseline Setup (W1-W2)
ITERATION 0: Baseline Proof-of-Concept
1.1 | Team Formation & Role Assignment | Group | 1.5A | 1 | 02/02 | 02/02 | ▬
1.2 | Initial Research Scoping & Topic Selection | Group | 4.4A | 1 | 02/02 | 02/02 | ▬
1.3 | Literature Review (10+ papers each) | ALL | 4.4A | 7 | 02/02 | 02/09 | █ | ▬
1.4 | Environment Setup: UV + CUDA on L40S server | Aron | 7.3A | 3 | 02/04 | 02/06 | ▬
1.5 | Create Trello Board & Research Backlog | Danil (SM) | 1.5A | 2 | 02/04 | 02/05 | ▬
1.6 | Create Gantt Chart | Aron | 1.5A | 2 | 02/04 | 02/06 | ▬
1.7 | Define 5 Individual Sub-Questions | ALL | 4.4A | 3 | 02/04 | 02/06 | ▬
1.8 | Install Face-Swap Models (InsightFace/Ghost) | Filipp | 7.3A | 2 | 02/09 | 02/10 |  | ▬
1.9 | Install RVC Voice Conversion Pipeline | Alex | 7.3A | 2 | 02/09 | 02/10 |  | ▬
1.10 | Install Metrics Suite (SSIM, FID, PSNR, WER, CosSim) | Aron + Maksym | 7.3A | 2 | 02/09 | 02/10 |  | ▬
1.11 | Ethics Application (Task 4) | ALL | 3.5 | 2 | 02/09 | 02/10 |  | ▬
1.12 | Data Management Plan (Task 4) | Aron | 3.5 | 2 | 02/09 | 02/10 |  | ▬
1.13 | Dataset Preparation: FakeAVCeleb (20 videos) | Aron + Danil | 4.4B | 3 | 02/09 | 02/11 |  | ▬
1.14 | Baseline: Wav2Lip + Whisper (20 videos) | ALL | 4.4B | 3 | 02/09 | 02/11 |  | ▬
1.15 | Baseline Metrics: AV Sync & Visual Quality | Maksym + Aron | 4.4B | 2 | 02/11 | 02/12 |  | ▬
1.16 | Baseline EDA Notebooks (individual) | ALL | 4.4B | 3 | 02/11 | 02/13 |  | ▬
M1 | ⚡ DEADLINE: Task 1 Submission (Gantt + Trello) | Group | 1.5A |  | 02/09 | 02/09
1.17 | Research Proposal Draft (optional) | ALL | 11.2 | 3 | 02/11 | 02/13 |  | ▬
M2 | 📝 OPTIONAL: Proposal Draft Submission | ALL | 11.2 |  | 02/13 | 02/13
✓0 | ITERATION 0 COMPLETE: Baseline Established | Group |  |  | 02/13
| SPRING BREAK (Feb 14-22) — ENJOY 🏖️ |  |  |  | 02/14 | 02/22 |  |  | 🏖️
SPRINT 2: Pipeline Analysis & Proposals (W3-W4)
ITERATION 1: Comprehensive Model Comparison
2.1 | Finalize Individual Research Proposals | ALL | 11.2 | 3 | 02/23 | 02/25 |  |  |  | ▬
2.2 | Face-Swap Architecture Testing (lightweight vs heavy) | Filipp | 7.3A | 3 | 02/23 | 02/25 |  |  |  | ▬
2.3 | RVC Pipeline: Buffer Size Experiments Setup | Alex | 7.3A | 3 | 02/23 | 02/25 |  |  |  | ▬
2.4 | Metrics Pipeline Validation & Calibration | Maksym + Aron | 7.3A | 2 | 02/23 | 02/24 |  |  |  | ▬
2.5 | Quantization Baseline Setup (FP32 profiling) | Aron | 7.3A | 3 | 02/23 | 02/25 |  |  |  | ▬
2.6 | Expand Dataset to 100 Videos | Aron + Danil | 4.4B | 2 | 02/23 | 02/24 |  |  |  | ▬
M3 | 📄 DEADLINE: Final Proposal + EDA Submission | ALL | 4.4,11.2 |  | 02/27 | 02/27
2.7A | Danil: MOS Survey Design & Pilot Study | Danil | 7.3B | 5 | 03/02 | 03/06 |  |  |  |  | █
| └─ Visual Fidelity × AV Latency → Perceived Naturalness | Danil
2.7B | Filipp: Lightweight vs Heavy Face-Swap FPS/Quality | Filipp | 7.3B | 5 | 03/02 | 03/06 |  |  |  |  | █
| └─ Inference speed (FPS) vs FID/SSIM across architectures | Filipp
2.7C | Alex: RVC Buffer/Chunk Length vs CosSim & Latency | Alex | 7.3B | 5 | 03/02 | 03/06 |  |  |  |  | █
| └─ Input buffer size impact on voice similarity & latency | Alex
2.7D | Maksym: PSNR/SSIM vs MOS Correlation Analysis | Maksym | 7.3B | 5 | 03/02 | 03/06 |  |  |  |  | █
| └─ Objective metrics vs subjective ratings correlation | Maksym
2.7E | Aron: PTQ FP32 vs INT8 on Primary Pipeline | Aron | 7.3B | 5 | 03/02 | 03/06 |  |  |  |  | █
| └─ Quantization impact on latency, memory, accuracy | Aron
✓1 | ITERATION 1 COMPLETE: Pipelines Characterized | Group |  |  | 03/06
SPRINT 3: Deep Experiments & Statistics (W5-W6)
ITERATION 2: Deep Dive & Hypothesis Testing
3.1A | Danil: Full MOS Study (20-30 participants) | Danil | 7.3B | 7 | 03/09 | 03/17 | [5 empty] | █ | ▬
| └─ Acceptability threshold, perception vs latency | Danil
3.1B | Filipp: FPS Sweep (15/20/25/30) & Quality Curves | Filipp | 7.3B | 5 | 03/09 | 03/13 | [5 empty] | █
| └─ Quality-speed tradeoff curves per architecture | Filipp
3.1C | Alex: Chunk Length Sweep & Latency Profiling | Alex | 7.3B | 5 | 03/09 | 03/13 | [5 empty] | █
| └─ Buffer optimization, real-time voice conversion | Alex
3.1D | Maksym: Metric-MOS Regression & ROC Analysis | Maksym | 7.3B | 5 | 03/09 | 03/13 | [5 empty] | █
| └─ Which objective metrics predict human perception? | Maksym
3.1E | Aron: INT8 Quantization + TensorRT Experiments | Aron | 7.3B | 5 | 03/09 | 03/13 | [5 empty] | █
| └─ FP32→FP16→INT8 quality degradation & speedup | Aron
3.2 | Statistical Analysis: All Sub-Questions (ILO 7.3C) | ALL | 7.3C | 5 | 03/13 | 03/19 | [5 empty] | ▬ | █
3.3 | Hypothesis Testing per Individual Research Question | ALL | 7.3C | 4 | 03/16 | 03/19 | [6 empty] | █
3.4 | Visualization: Quality-Latency Tradeoff Plots | ALL | 7.3B | 3 | 03/16 | 03/18 | [6 empty] | ▬
M4 | 📝 STATISTICS MOCK EXAM (W6 Wed Mar 18, 10:00) | ALL | 0.3 |  | 03/18 | 03/18
✓2 | ITERATION 2 COMPLETE: Experiments & Analysis Done | Group |  |  | 03/20
SPRINT 4: Synthesis & Presentation (W7-W8)
ITERATION 3: Final Synthesis & Communication
4.1 | Research Notebook Section 4: Synthesis (ILO 7.3D) | ALL | 7.3D | 5 | 03/23 | 03/27 | [7 empty] | █
4.2 | Limitations & Assumptions Documentation | ALL | 7.3D | 3 | 03/23 | 03/25 | [7 empty] | ▬
4.3 | Future Directions & Recommendations | ALL | 7.3D | 3 | 03/25 | 03/27 | [7 empty] | ▬
M5 | 📝 STATISTICS EXAM (W7 Wed Mar 25, 10:00-11:30) | ALL | 0.3 |  | 03/25 | 03/25
4.4 | Presentation Structure & Slide Creation | Group | 10.2 | 3 | 03/30 | 04/01 | [8 empty] | █
4.5 | Individual Slide Sections (5-7 slides each) | ALL | 10.2 | 3 | 03/30 | 04/01 | [8 empty] | █
4.6 | Presentation Practice & Rehearsal | Group | 10.2 | 1 | 03/31 | 03/31 | [8 empty] | ▬
4.7 | Final Research Notebook Polish | ALL | 7.3 | 3 | 03/30 | 04/01 | [8 empty] | ▬
M6 | 🎤 FINAL PRESENTATIONS (W8 Wed Apr 1) | Group | 10.2 |  | 04/01 | 04/01
M7 | 🏁 FINAL SUBMISSION (W8 Thu Apr 2, 17:00) | ALL | ALL |  | 04/02 | 04/02
✓3 | PROJECT COMPLETE | Group |  |  | 04/02

## Iteration Details
Iteration | Timeline | Primary Goal | Deliverables | Can Stop? | Key Metrics | Person Focus
Iter 0 | W1-W2 | Baseline: Wav2Lip + Whisper (20 videos) | • Baseline pipeline functional • Basic metrics collected • EDA notebooks • Gantt + Trello (Task 1) | ✅ Minimal | • Latency, FPS • PSNR, SSIM • LED, Sync-C • WER, CosSim | • Danil: SM + risk logs • Filipp: Face-swap install • Alex: RVC install • Maksym: Metrics suite • Aron: Env setup + data mgmt
Iter 1 | W3-W4 | Full pipeline matrix + individual experiments begin | • Research proposals submitted • All pipelines tested • Individual experiment tracks active • Research notebook Sections 1-2 | ✅ Good | • All baseline + • FID, LPIPS, CSIM • Per-component latency • Individual sub-Q metrics | • Danil: MOS pilot • Filipp: Architecture FPS/quality • Alex: Buffer experiments • Maksym: Metric correlation • Aron: FP32 profiling + INT8
Iter 2 | W5-W6 | Deep dive: experiments, stats, hypothesis testing | • All experiments completed • Statistical analysis done • Hypotheses tested • Research notebook Section 3 | ✅ Strong | • Optimization metrics • MOS scores • Correlation coefficients • ANOVA/t-test results | • Danil: Full MOS study • Filipp: FPS sweep • Alex: Chunk sweep • Maksym: ROC/regression • Aron: FP32→FP16→INT8 curves
Iter 3 | W7-W8 | Synthesis, presentation, final submission | • Complete notebooks (4 sections) • Final presentation • All ILOs evidenced • Learning log complete | ✅ Complete | • All metrics synthesized • Cross-study insights • Deployment recommendations | • All: Notebooks + slides • Group: Integrated presentation • Each: 5-7 slides on sub-study

## Person Assignments
Name | Role | Sub-Question | Research Focus | Models/Tools | Primary Metrics | Statistical Methods | Deliverables | Timeline
Danil Sysenko | QA/PM Scrum Master Sprint 1 | How does the trade-off between Visual Fidelity and AV Latency impact the Perceived Naturalness (MOS)? | User Perception Study • MOS survey (20-30 participants) • Acceptability thresholds • Visual fidelity × latency interaction | • All team pipelines • MOS survey tool • Multiple quality levels | • MOS (1-5 scale) • Acceptability rate (%) • Detection rate • Inter-rater reliability | • Pearson/Spearman correlation • Logistic regression • ROC curves • Cronbach's alpha | • Research proposal • EDA notebook • Research notebook (4 sections) • 5-7 presentation slides | W1-2: SM + setup W3-4: Survey pilot W5-6: Full study W7-8: Analysis + pres
Filipp Lotsmanov | Video Lead Scrum Master Sprint 2 | What is the trade-off between inference speed (FPS) and visual quality (FID/SSIM) comparing lightweight vs heavy face-swap architectures? | Visual Fidelity Analysis • Architecture comparison • FPS sweep (15/20/25/30) • Quality-speed tradeoff curves | • InsightFace/Ghost • MuseTalk • LivePortrait • Wav2Lip (baseline) | • FPS achieved • FID (distribution) • SSIM (structural) • CSIM (identity) • LPIPS (perceptual) | • ANOVA (architecture effect) • Post-hoc tests • Regression (FPS vs quality) • Pareto frontier | • Research proposal • EDA notebook • Research notebook (4 sections) • 5-7 presentation slides | W1-2: Model install W3-4: SM + baselines W5-6: FPS sweep W7-8: Analysis + pres
Alex Krasnoshtanov | Audio Lead Scrum Master Sprint 3 | How does the input buffer size (chunk length) impact voice similarity (CosSim) and processing latency in RVC-based conversion? | Audio Similarity & Latency • RVC/VITS pipeline • Buffer/chunk optimization • Latency vs quality tradeoff | • RVC pipeline • VITS model • Multiple chunk sizes • Whisper (ASR for WER) | • Cosine Similarity • WER (Word Error Rate) • Audio latency (ms) • MCD (Mel Cepstral Dist) | • T-tests (buffer comparisons) • Effect size (Cohen's d) • Regression (chunk vs latency) • Correlation analysis | • Research proposal • EDA notebook • Research notebook (4 sections) • 5-7 presentation slides | W1-2: RVC install W3-4: Buffer setup W5-6: SM + sweeps W7-8: Analysis + pres
Maksym Steshkin | Video Support & Metrics Scrum Master Sprint 4 | To what extent do standard objective metrics (PSNR, SSIM) correlate with human subjective ratings (MOS) in real-time video synthesis? | Metric Validation • Objective vs subjective correlation • Metric sensitivity analysis • Best predictor identification | • MediaPipe (baseline) • All team pipelines • scikit-learn • Objective metric suite | • PSNR vs MOS corr. • SSIM vs MOS corr. • FID vs MOS corr. • Correlation coefficients | • Pearson/Spearman • ROC analysis • Multiple regression • Cross-validation • Metric ranking | • Research proposal • EDA notebook • Research notebook (4 sections) • 5-7 presentation slides | W1-2: Metrics impl. W3-4: Baseline metrics W5-6: Correlation study W7-8: SM + analysis + pres
Aron Wojciechowicz | Infrastructure & Audio Support Research Chair / Evaluator | How does Post-Training Quantization (FP32 vs. INT8) impact the trade-off between Inference Latency, Memory Footprint, and Model Accuracy? | System Efficiency & Optimization • PTQ: FP32 → FP16 → INT8 • Latency profiling • Memory footprint analysis • Quality degradation measurement | • PyTorch quantization • TensorRT • ONNX Runtime • nvidia-smi profiling • L40S GPUs (CUDA 12.8) | • Inference latency (ms) • Memory usage (GB) • Speedup ratio • Quality degradation % • SSIM/PSNR delta | • Paired t-tests (FP32 vs INT8) • Effect size (Cohen's d) • Cost-benefit analysis • Tradeoff curve fitting | • Research proposal • EDA notebook • Research notebook (4 sections) • 5-7 presentation slides | W1-2: Env + data mgmt W3-4: FP32 profiling W5-6: Quantization exp. W7-8: Analysis + pres

## Metrics Reference
Category | Metric | Description | Unit | Formula/Method | Tool/Library | Used By | Interpretation
Audio | Cosine Similarity | Speaker embedding similarity (source vs converted) | Score (0-1) | Cosine sim of speaker embeddings | resemblyzer, speechbrain | Alex (primary), Aron | Higher = better. >0.85 = good
Audio | WER | Word Error Rate of converted speech | % | ASR transcript comparison | Whisper, jiwer | Alex (primary), All | Lower = better. <10% = good
Audio | Audio Latency | Time for voice conversion processing | ms | End-to-end timing | time.time(), PyTorch profiler | Alex + Aron (primary) | Lower = better. <100ms target
Visual | FPS | Frames per second achieved | frames/s | 1 / avg_frame_time | time.time() | Filipp (primary), All | 30fps = real-time target
Visual | FID | Fréchet Inception Distance | Score (lower=better) | Fréchet dist of Inception features | pytorch-fid | Filipp (primary), Maksym | <50 = good, <20 = excellent
Visual | SSIM | Structural Similarity Index | Score (0-1) | Luminance+contrast+structure | scikit-image | Filipp + Maksym (primary) | >0.9 = good quality
Visual | PSNR | Peak Signal-to-Noise Ratio | dB | 10*log10(MAX²/MSE) | scikit-image | Maksym (primary), All | >30dB = good quality
Visual | LPIPS | Learned Perceptual Similarity | Score (0-1) | VGG feature distance | lpips package | Filipp, Maksym | <0.3 = good quality
Visual | CSIM | Identity Preservation | Score (0-1) | ArcFace embedding cosine sim | insightface | Filipp (primary) | >0.8 = good preservation
AV Sync | LED | Lip Error Distance | pixels | L2 dist of lip keypoints | dlib, MediaPipe | Danil, Maksym | <10px = good sync
AV Sync | Sync-C | Synchronization Confidence | Score (0-10) | SyncNet discriminator output | SyncNet (pretrained) | Danil, Maksym | >8 = excellent sync
Perceptual | MOS | Mean Opinion Score | Score (1-5) | Mean of human ratings | Survey platform | Danil (primary), Maksym | 5=excellent, 3=acceptable
Perceptual | Acceptability | Threshold for acceptable quality | ms / % | ROC analysis | sklearn | Danil (primary) | Critical for deployment
Efficiency | Speedup Ratio | Optimization performance gain | Ratio (e.g. 2.5x) | baseline_time / optimized_time | Custom | Aron (primary) | >2x = good, >5x = excellent
Efficiency | Quality Degradation % | Quality loss from quantization | % | (baseline-opt)/baseline*100 | Custom | Aron (primary) | <5% = acceptable, <10% = tolerable
Efficiency | Memory Footprint | GPU memory usage | GB | nvidia-smi / torch profiler | nvidia-smi, PyTorch | Aron (primary) | Lower = better for deployment

## Model Architecture
Component | Model | Architecture | Input | Output | Latency | Key Strengths | Key Limitations | Used By
Audio Encoder | Whisper (Small) | Transformer enc-dec (ASR) | Audio 16kHz | Embeddings (768-dim) | ~20-40ms | Robust, multilingual | Optimized for ASR not sync | All (baseline)
Audio Encoder | Wav2Vec2-BERT | Transformer enc (SSL) | Audio 16kHz | Embeddings (1024-dim) | ~15-30ms | Acoustic features, efficient | Less semantic understanding | Alex, comparison
Voice Conversion | RVC Pipeline | Retrieval + VITS | Source audio + model | Converted voice | ~50-200ms | High similarity, flexible | Buffer/chunk latency tradeoff | Alex (primary)
Face Swap | InsightFace/Ghost | GAN-based face swap | Source + target face | Swapped face video | ~30-50ms/frame | High fidelity, identity swap | Compute intensive | Filipp (primary)
Visual Gen | MuseTalk | VAE + UNet (latent) | Audio + ref image | Video (256×256) | ~30-40ms/frame | High quality, real-time capable | Resolution limited | All, Aron (quant)
Visual Gen | Wav2Lip | GAN + sync disc | Audio MFCC + video | Video (96-192px) | ~25-35ms/frame | Excellent lip-sync | Lower visual quality | All (baseline)
Visual Gen | LivePortrait | Implicit keypoint | Audio + driving src | Animated portrait | ~35-45ms/frame | Temporal consistency | Slower | Filipp, comparison
Baseline Pipeline | Whisper + Wav2Lip | Encoder → Generator | Audio waveform | Lip-synced video | ~45-75ms total | Proven, documented | Not optimal | All (Iteration 0)

## Resource Planning
Week | Phase | Computation Type | Est. GPU Hours | Priority | Notes
W1 | Setup & Testing | Light - install tests | 2-3 | Medium | UV env setup, install models on L40S. Aron leads infra.
W2 | Iteration 0 Baseline | Moderate - 20 videos | 5-8 | High | Wav2Lip + Whisper baseline. Critical for proposal.
W3 | Proposals + Setup | Light - model testing | 3-5 | High | All 5 sub-question setups validated. Proposals due Fri.
W4 | Iteration 1 Execution | HEAVY - experiments | 20-30 | CRITICAL | All 5 individual experiment tracks running. Batch overnight.
W5 | Iteration 2 Deep Dive | Heavy - sweeps | 15-20 | High | FPS sweeps, buffer sweeps, quantization (FP16/INT8), MOS gen.
W6 | Analysis & Stats | Light - compute | 3-5 | Medium | Statistical analysis, visualization. Mock exam Wed.
W7 | Synthesis | Light - verification | 2-4 | Low | Final checks, missing data. Stats exam Wed.
W8 | Final Polish | Minimal - spot checks | 1-2 | Low | Presentation prep. Final submission Thu.
TOTAL |  |  | 51-77 |  | Peak usage W4-W5. L40S server (8× GPUs, 46GB each).